## Sprint Master Plan
Story ID | Title | Epic | Priority | Story Points | Sprint | Owner | Risk Level | Start Date | End Date | Est. Days | Progress % | Blockers | Status | Dependencies | Notes
US-001 | User Story 1 | Data Processing | P1 | 3 | Sprint 2 | Vijay Ughade | Medium | 04/07/2026 | 04/11/2026 | 4 | 2% | Waiting for input | Done | Blocked by data availability | Notes for US-001
US-002 | User Story 2 | EDA | P3 | 21 | Sprint 2 | Anjali Waghmare | Low | 03/29/2026 | 04/03/2026 | 5 | 100% | Waiting for input | In Review | None | Notes for US-002
US-003 | User Story 3 | EDA | P1 | 3 | Sprint 3 | Anjali Waghmare | Medium | 03/29/2026 | 03/31/2026 | 2 | 27% | Dependencies pending | In Review | Depends on US-001, US-001 | Notes for US-003
US-004 | User Story 4 | QA | P0 | 5 | Sprint 2 | Sahil Betal | Low | 03/23/2026 | 03/24/2026 | 1 | 0% | To Be Determined | Not Started | Depends on US-001 | Notes for US-004
US-005 | User Story 5 | EDA | P2 | 21 | Sprint 4 | Maithili Wagh | High | 03/20/2026 | 03/24/2026 | 4 | 7% | To Be Determined | Done | Awaiting stakeholder approval | Notes for US-005
US-006 | User Story 6 | QA | P1 | 21 | Sprint 5 | Maithili Wagh | Low | 03/26/2026 | 03/30/2026 | 4 | 9% | To Be Determined | In Progress | Blocked by API design | Notes for US-006
US-007 | User Story 7 | Data Processing | P3 | 21 | Sprint 4 | Vijay Ughade | Critical | 03/24/2026 | 03/28/2026 | 4 | 0% | None | Not Started | Depends on US-006 | Notes for US-007
US-008 | User Story 8 | EDA | P2 | 8 | Sprint 4 | Anjali Waghmare | Low | 04/03/2026 | 04/07/2026 | 4 | 76% | Waiting for input | In Review | Blocked by requirements finalization | Notes for US-008
US-009 | User Story 9 | Data Setup | P1 | 3 | Sprint 3 | Maithili Wagh | Critical | 03/29/2026 | 03/30/2026 | 1 | 0% | To Be Determined | Not Started | Blocked by infrastructure setup | Notes for US-009
US-010 | User Story 10 | QA | P0 | 3 | Sprint 1 | Sahil Betal | Low | 04/04/2026 | 04/06/2026 | 2 | 17% | Dependencies pending | Done | Blocked by infrastructure setup | Notes for US-010
US-011 | User Story 11 | Modeling | P1 | 21 | Sprint 2 | Sahil Betal | Medium | 03/19/2026 | 03/24/2026 | 5 | 73% | To Be Determined | In Progress | Blocked by requirements finalization | Notes for US-011
US-012 | User Story 12 | QA | P0 | 8 | Sprint 1 | Sahil Betal | High | 03/23/2026 | 03/25/2026 | 2 | 79% | None | In Review | Blocked by API design | Notes for US-012
US-013 | User Story 13 | Visualization | P3 | 8 | Sprint 3 | Vijay Ughade | High | 04/05/2026 | 04/06/2026 | 1 | 0% | To Be Determined | Not Started | Blocked by requirements finalization | Notes for US-013
US-014 | User Story 14 | Data Setup | P1 | 5 | Sprint 5 | Maithili Wagh | Medium | 03/24/2026 | 03/27/2026 | 3 | 0% | Dependencies pending | Not Started | Depends on US-013, US-004 | Notes for US-014
US-015 | User Story 15 | Visualization | P3 | 21 | Sprint 1 | Vijay Ughade | Critical | 03/18/2026 | 03/21/2026 | 3 | 57% | To Be Determined | In Review | Depends on Visualization completion | Notes for US-015
US-016 | User Story 16 | Documentation | P2 | 5 | Sprint 4 | Vijay Ughade | Critical | 03/19/2026 | 03/20/2026 | 1 | 79% | To Be Determined | In Progress | Blocked by external dependency | Notes for US-016
US-017 | User Story 17 | QA | P0 | 3 | Sprint 5 | Sahil Betal | Medium | 03/25/2026 | 03/29/2026 | 4 | 50% | Waiting for input | In Review | Blocked by data availability | Notes for US-017
US-018 | User Story 18 | Insights | P0 | 5 | Sprint 2 | Vijay Ughade | Critical | 04/07/2026 | 04/09/2026 | 2 | 57% | Waiting for input | In Progress | Depends on Insights completion | Notes for US-018
US-019 | User Story 19 | Visualization | P0 | 5 | Sprint 2 | Vijay Ughade | Medium | 04/07/2026 | 04/12/2026 | 5 | 0% | None | Not Started | None | Notes for US-019
US-020 | User Story 20 | Documentation | P0 | 3 | Sprint 4 | Sahil Betal | Low | 03/27/2026 | 03/30/2026 | 3 | 61% | To Be Determined | In Review | Depends on US-019 | Notes for US-020
US-021 | User Story 21 | Modeling | P1 | 13 | Sprint 4 | Maithili Wagh | Low | 04/06/2026 | 04/08/2026 | 2 | 38% | Dependencies pending | In Progress | Blocked by data availability | Notes for US-021
US-022 | User Story 22 | EDA | P1 | 8 | Sprint 4 | Maithili Wagh | Medium | 03/30/2026 | 04/04/2026 | 5 | 0% | Dependencies pending | Not Started | Blocked by infrastructure setup | Notes for US-022
US-023 | User Story 23 | Insights | P0 | 5 | Sprint 1 | Maithili Wagh | Medium | 03/21/2026 | 03/22/2026 | 1 | 70% | Dependencies pending | In Progress | Depends on US-021, US-017 | Notes for US-023
US-024 | User Story 24 | QA | P2 | 13 | Sprint 3 | Maithili Wagh | Critical | 03/28/2026 | 04/02/2026 | 5 | 95% | Dependencies pending | Done | Blocked by data availability | Notes for US-024
US-025 | User Story 25 | Data Setup | P3 | 13 | Sprint 5 | Maithili Wagh | Medium | 03/24/2026 | 03/25/2026 | 1 | 0% | To Be Determined | Not Started | Blocked by data availability | Notes for US-025
US-026 | User Story 26 | Documentation | P2 | 21 | Sprint 2 | Sahil Betal | Critical | 03/25/2026 | 03/29/2026 | 4 | 27% | Dependencies pending | In Review | Blocked by infrastructure setup | Notes for US-026
US-027 | User Story 27 | Modeling | P1 | 8 | Sprint 3 | Vijay Ughade | High | 03/25/2026 | 03/26/2026 | 1 | 51% | Waiting for input | In Review | Depends on US-024 | Notes for US-027
US-028 | User Story 28 | Documentation | P0 | 13 | Sprint 5 | Sahil Betal | Medium | 03/29/2026 | 04/01/2026 | 3 | 20% | None | In Review | Depends on US-018 | Notes for US-028
US-029 | User Story 29 | Data Processing | P1 | 3 | Sprint 1 | Anjali Waghmare | Medium | 04/03/2026 | 04/05/2026 | 2 | 0% | None | Not Started | Depends on Data Processing completion | Notes for US-029
US-030 | User Story 30 | Data Processing | P2 | 5 | Sprint 4 | Sahil Betal | High | 03/26/2026 | 03/29/2026 | 3 | 30% | To Be Determined | Done | Depends on Data Processing completion | Notes for US-030
US-031 | User Story 31 | EDA | P0 | 13 | Sprint 4 | Anjali Waghmare | Medium | 03/27/2026 | 04/01/2026 | 5 | 0% | Dependencies pending | Not Started | Awaiting stakeholder approval | Notes for US-031
US-032 | User Story 32 | Data Setup | P1 | 13 | Sprint 2 | Maithili Wagh | Medium | 03/30/2026 | 04/03/2026 | 4 | 26% | Dependencies pending | In Progress | None | Notes for US-032
US-033 | User Story 33 | Data Setup | P1 | 21 | Sprint 3 | Maithili Wagh | High | 03/20/2026 | 03/24/2026 | 4 | 0% | None | Not Started | Blocked by requirements finalization | Notes for US-033
US-034 | User Story 34 | Visualization | P1 | 13 | Sprint 4 | Anjali Waghmare | Medium | 04/01/2026 | 04/04/2026 | 3 | 0% | Waiting for input | Not Started | Awaiting stakeholder approval | Notes for US-034
US-035 | User Story 35 | Visualization | P2 | 8 | Sprint 5 | Sahil Betal | Medium | 04/01/2026 | 04/02/2026 | 1 | 16% | Dependencies pending | In Progress | Depends on Visualization completion | Notes for US-035
US-036 | User Story 36 | Documentation | P0 | 21 | Sprint 5 | Maithili Wagh | High | 04/02/2026 | 04/04/2026 | 2 | 52% | None | In Progress | Awaiting stakeholder approval | Notes for US-036
US-037 | User Story 37 | Data Setup | P0 | 5 | Sprint 1 | Maithili Wagh | Low | 04/02/2026 | 04/05/2026 | 3 | 59% | Waiting for input | Done | Depends on Data Setup completion | Notes for US-037
US-038 | User Story 38 | EDA | P2 | 21 | Sprint 2 | Vijay Ughade | High | 04/04/2026 | 04/09/2026 | 5 | 97% | Waiting for input | In Progress | Depends on EDA completion | Notes for US-038
US-039 | User Story 39 | Documentation | P0 | 5 | Sprint 3 | Vijay Ughade | High | 03/25/2026 | 03/29/2026 | 4 | 58% | Dependencies pending | In Progress | Blocked by requirements finalization | Notes for US-039
US-040 | User Story 40 | QA | P0 | 3 | Sprint 4 | Sahil Betal | Low | 03/30/2026 | 04/02/2026 | 3 | 14% | None | Done | Blocked by external dependency | Notes for US-040
US-041 | User Story 41 | Data Setup | P1 | 13 | Sprint 5 | Anjali Waghmare | Medium | 03/29/2026 | 03/31/2026 | 2 | 9% | To Be Determined | In Progress | Depends on US-033 | Notes for US-041
US-042 | User Story 42 | Data Setup | P0 | 5 | Sprint 2 | Anjali Waghmare | Low | 04/02/2026 | 04/07/2026 | 5 | 71% | Dependencies pending | In Progress | Depends on US-041, US-032 | Notes for US-042
US-043 | User Story 43 | Visualization | P0 | 21 | Sprint 4 | Anjali Waghmare | High | 04/02/2026 | 04/07/2026 | 5 | 18% | To Be Determined | In Review | Awaiting stakeholder approval | Notes for US-043
US-044 | User Story 44 | Data Processing | P3 | 3 | Sprint 3 | Sahil Betal | Low | 04/06/2026 | 04/10/2026 | 4 | 0% | To Be Determined | Not Started | None | Notes for US-044
US-045 | User Story 45 | Data Processing | P1 | 5 | Sprint 2 | Maithili Wagh | Medium | 03/25/2026 | 03/30/2026 | 5 | 53% | None | Done | Blocked by external dependency | Notes for US-045
US-046 | User Story 46 | Modeling | P2 | 3 | Sprint 5 | Vijay Ughade | Low | 04/03/2026 | 04/08/2026 | 5 | 0% | None | Not Started | Blocked by requirements finalization | Notes for US-046
US-047 | User Story 47 | QA | P1 | 3 | Sprint 4 | Anjali Waghmare | High | 03/29/2026 | 04/03/2026 | 5 | 73% | Dependencies pending | In Progress | Depends on QA completion | Notes for US-047
US-048 | User Story 48 | Data Setup | P3 | 21 | Sprint 1 | Anjali Waghmare | Medium | 03/30/2026 | 03/31/2026 | 1 | 14% | Dependencies pending | In Review | None | Notes for US-048
US-049 | User Story 49 | QA | P0 | 21 | Sprint 1 | Sahil Betal | Low | 04/05/2026 | 04/10/2026 | 5 | 64% | Dependencies pending | In Review | Depends on US-048 | Notes for US-049
US-050 | User Story 50 | Modeling | P2 | 3 | Sprint 3 | Sahil Betal | Medium | 03/29/2026 | 04/01/2026 | 3 | 38% | Waiting for input | In Progress | Awaiting stakeholder approval | Notes for US-050
US-051 | User Story 51 | Modeling | P0 | 3 | Sprint 2 | Sahil Betal | Low | 03/23/2026 | 03/28/2026 | 5 | 0% | None | Not Started | None | Notes for US-051
US-052 | User Story 52 | QA | P3 | 21 | Sprint 3 | Maithili Wagh | Medium | 03/21/2026 | 03/26/2026 | 5 | 70% | To Be Determined | In Review | None | Notes for US-052
US-053 | User Story 53 | EDA | P3 | 8 | Sprint 5 | Vijay Ughade | Critical | 03/25/2026 | 03/28/2026 | 3 | 59% | Waiting for input | In Progress | Depends on US-043 | Notes for US-053
US-054 | User Story 54 | Data Processing | P2 | 5 | Sprint 4 | Maithili Wagh | Critical | 03/29/2026 | 03/30/2026 | 1 | 29% | None | In Progress | Depends on US-048, US-038 | Notes for US-054
US-055 | User Story 55 | Modeling | P0 | 8 | Sprint 3 | Vijay Ughade | Critical | 03/24/2026 | 03/29/2026 | 5 | 43% | Waiting for input | In Review | None | Notes for US-055
US-056 | User Story 56 | Documentation | P2 | 8 | Sprint 2 | Sahil Betal | High | 03/22/2026 | 03/25/2026 | 3 | 27% | Waiting for input | In Review | Depends on US-044, US-048 | Notes for US-056
US-057 | User Story 57 | Visualization | P3 | 3 | Sprint 5 | Anjali Waghmare | Low | 03/31/2026 | 04/02/2026 | 2 | 62% | None | Done | Depends on US-052, US-056 | Notes for US-057
US-058 | User Story 58 | Data Processing | P0 | 3 | Sprint 4 | Anjali Waghmare | Low | 03/18/2026 | 03/19/2026 | 1 | 48% | Waiting for input | In Review | Depends on Data Processing completion | Notes for US-058
US-059 | User Story 59 | Modeling | P1 | 8 | Sprint 3 | Maithili Wagh | Critical | 03/24/2026 | 03/29/2026 | 5 | 0% | Waiting for input | Not Started | Depends on Modeling completion | Notes for US-059
US-060 | User Story 60 | EDA | P3 | 13 | Sprint 4 | Anjali Waghmare | Medium | 03/23/2026 | 03/25/2026 | 2 | 0% | None | Not Started | Depends on US-046, US-059 | Notes for US-060
US-061 | User Story 61 | Insights | P3 | 3 | Sprint 2 | Maithili Wagh | High | 03/28/2026 | 03/31/2026 | 3 | 47% | None | Done | Blocked by API design | Notes for US-061
US-062 | User Story 62 | Modeling | P2 | 21 | Sprint 2 | Vijay Ughade | Low | 03/30/2026 | 03/31/2026 | 1 | 87% | Dependencies pending | In Progress | Depends on US-060 | Notes for US-062
US-063 | User Story 63 | Data Processing | P0 | 13 | Sprint 4 | Vijay Ughade | Low | 04/01/2026 | 04/06/2026 | 5 | 67% | None | In Review | Awaiting stakeholder approval | Notes for US-063
US-064 | User Story 64 | Visualization | P0 | 21 | Sprint 3 | Anjali Waghmare | Critical | 03/19/2026 | 03/21/2026 | 2 | 44% | Dependencies pending | Done | Blocked by infrastructure setup | Notes for US-064
US-065 | User Story 65 | Documentation | P0 | 13 | Sprint 4 | Sahil Betal | Critical | 04/01/2026 | 04/03/2026 | 2 | 24% | Dependencies pending | Done | Blocked by requirements finalization | Notes for US-065
US-066 | User Story 66 | QA | P1 | 21 | Sprint 4 | Maithili Wagh | High | 03/31/2026 | 04/02/2026 | 2 | 81% | Dependencies pending | Done | Blocked by data availability | Notes for US-066
US-067 | User Story 67 | Documentation | P0 | 8 | Sprint 3 | Anjali Waghmare | Low | 03/28/2026 | 03/29/2026 | 1 | 0% | Dependencies pending | Not Started | Awaiting stakeholder approval | Notes for US-067
US-068 | User Story 68 | Data Setup | P0 | 8 | Sprint 1 | Vijay Ughade | Medium | 04/04/2026 | 04/09/2026 | 5 | 93% | Dependencies pending | In Review | Blocked by requirements finalization | Notes for US-068
US-069 | User Story 69 | Modeling | P2 | 13 | Sprint 1 | Anjali Waghmare | Medium | 04/05/2026 | 04/10/2026 | 5 | 35% | Dependencies pending | In Review | Blocked by external dependency | Notes for US-069
US-070 | User Story 70 | Data Setup | P1 | 3 | Sprint 2 | Anjali Waghmare | Low | 03/26/2026 | 03/28/2026 | 2 | 98% | Waiting for input | In Review | Blocked by API design | Notes for US-070
US-071 | User Story 71 | Documentation | P0 | 13 | Sprint 1 | Maithili Wagh | High | 03/26/2026 | 03/28/2026 | 2 | 0% | None | Not Started | Awaiting stakeholder approval | Notes for US-071
US-072 | User Story 72 | Documentation | P0 | 3 | Sprint 1 | Sahil Betal | Critical | 04/06/2026 | 04/08/2026 | 2 | 29% | Waiting for input | In Review | Blocked by external dependency | Notes for US-072
US-073 | User Story 73 | Data Processing | P1 | 3 | Sprint 3 | Anjali Waghmare | Low | 03/25/2026 | 03/27/2026 | 2 | 0% | To Be Determined | Not Started | Depends on US-072 | Notes for US-073
US-074 | User Story 74 | Insights | P1 | 21 | Sprint 2 | Sahil Betal | Critical | 04/06/2026 | 04/10/2026 | 4 | 0% | Dependencies pending | Not Started | Blocked by data availability | Notes for US-074
US-075 | User Story 75 | EDA | P3 | 3 | Sprint 4 | Vijay Ughade | Medium | 04/07/2026 | 04/10/2026 | 3 | 34% | None | In Review | Depends on US-068 | Notes for US-075
US-076 | User Story 76 | EDA | P1 | 5 | Sprint 4 | Sahil Betal | Critical | 04/07/2026 | 04/12/2026 | 5 | 0% | Waiting for input | Not Started | Blocked by API design | Notes for US-076
US-077 | User Story 77 | EDA | P1 | 3 | Sprint 5 | Maithili Wagh | Medium | 04/03/2026 | 04/07/2026 | 4 | 83% | Dependencies pending | In Review | None | Notes for US-077
US-078 | User Story 78 | Insights | P3 | 8 | Sprint 4 | Anjali Waghmare | Critical | 03/22/2026 | 03/23/2026 | 1 | 75% | To Be Determined | In Review | Awaiting stakeholder approval | Notes for US-078
US-079 | User Story 79 | Documentation | P2 | 8 | Sprint 1 | Anjali Waghmare | Low | 03/24/2026 | 03/27/2026 | 3 | 56% | Dependencies pending | Done | None | Notes for US-079
US-080 | User Story 80 | Data Processing | P0 | 13 | Sprint 3 | Maithili Wagh | Medium | 03/21/2026 | 03/22/2026 | 1 | 65% | Dependencies pending | In Review | None | Notes for US-080
US-081 | User Story 81 | Data Setup | P1 | 8 | Sprint 1 | Vijay Ughade | Low | 03/20/2026 | 03/24/2026 | 4 | 76% | None | In Review | Blocked by data availability | Notes for US-081
US-082 | User Story 82 | Visualization | P0 | 8 | Sprint 3 | Sahil Betal | Medium | 04/01/2026 | 04/03/2026 | 2 | 58% | Waiting for input | In Progress | Depends on Visualization completion | Notes for US-082
US-083 | User Story 83 | Data Setup | P0 | 3 | Sprint 4 | Maithili Wagh | Medium | 04/03/2026 | 04/08/2026 | 5 | 3% | To Be Determined | Done | Blocked by requirements finalization | Notes for US-083
US-084 | User Story 84 | Modeling | P0 | 21 | Sprint 2 | Sahil Betal | Medium | 03/25/2026 | 03/30/2026 | 5 | 0% | None | Done | Blocked by external dependency | Notes for US-084
US-085 | User Story 85 | Data Processing | P1 | 8 | Sprint 1 | Vijay Ughade | High | 04/06/2026 | 04/09/2026 | 3 | 67% | Waiting for input | Done | Depends on US-073, US-071 | Notes for US-085
US-086 | User Story 86 | Visualization | P3 | 8 | Sprint 3 | Anjali Waghmare | Critical | 04/04/2026 | 04/07/2026 | 3 | 1% | None | Done | Depends on US-077 | Notes for US-086
US-087 | User Story 87 | Data Setup | P3 | 21 | Sprint 2 | Vijay Ughade | Low | 03/26/2026 | 03/30/2026 | 4 | 13% | None | In Progress | Blocked by infrastructure setup | Notes for US-087
US-088 | User Story 88 | Visualization | P3 | 3 | Sprint 4 | Sahil Betal | Critical | 04/07/2026 | 04/08/2026 | 1 | 10% | Waiting for input | In Progress | Blocked by requirements finalization | Notes for US-088
US-089 | User Story 89 | Modeling | P0 | 3 | Sprint 3 | Vijay Ughade | Critical | 04/04/2026 | 04/09/2026 | 5 | 45% | To Be Determined | In Progress | Blocked by infrastructure setup | Notes for US-089
US-090 | User Story 90 | Insights | P3 | 8 | Sprint 5 | Sahil Betal | Critical | 04/05/2026 | 04/07/2026 | 2 | 43% | Waiting for input | Done | Blocked by infrastructure setup | Notes for US-090
US-091 | User Story 91 | Documentation | P3 | 8 | Sprint 5 | Anjali Waghmare | Critical | 04/03/2026 | 04/04/2026 | 1 | 0% | Dependencies pending | Not Started | Blocked by external dependency | Notes for US-091
US-092 | User Story 92 | QA | P3 | 8 | Sprint 2 | Maithili Wagh | Critical | 03/25/2026 | 03/30/2026 | 5 | 0% | Waiting for input | Not Started | Depends on QA completion | Notes for US-092
US-093 | User Story 93 | Data Processing | P0 | 3 | Sprint 1 | Maithili Wagh | Low | 03/27/2026 | 03/28/2026 | 1 | 83% | To Be Determined | Done | Depends on US-092 | Notes for US-093
US-094 | User Story 94 | Documentation | P1 | 13 | Sprint 2 | Maithili Wagh | Critical | 03/22/2026 | 03/25/2026 | 3 | 0% | Waiting for input | Not Started | Awaiting stakeholder approval | Notes for US-094
US-095 | User Story 95 | Documentation | P1 | 3 | Sprint 2 | Maithili Wagh | High | 04/02/2026 | 04/07/2026 | 5 | 0% | To Be Determined | Not Started | Depends on Documentation completion | Notes for US-095
US-096 | User Story 96 | Modeling | P3 | 21 | Sprint 4 | Sahil Betal | Medium | 03/27/2026 | 04/01/2026 | 5 | 0% | None | Not Started | Blocked by infrastructure setup | Notes for US-096
US-097 | User Story 97 | Insights | P3 | 3 | Sprint 3 | Maithili Wagh | High | 03/29/2026 | 03/31/2026 | 2 | 50% | To Be Determined | Done | Depends on US-085, US-081 | Notes for US-097
US-098 | User Story 98 | Data Processing | P1 | 8 | Sprint 2 | Anjali Waghmare | Low | 04/05/2026 | 04/09/2026 | 4 | 34% | To Be Determined | In Progress | Depends on US-093, US-094 | Notes for US-098
US-099 | User Story 99 | Visualization | P1 | 8 | Sprint 1 | Sahil Betal | High | 03/25/2026 | 03/29/2026 | 4 | 0% | None | Not Started | Blocked by data availability | Notes for US-099
US-100 | User Story 100 | Documentation | P1 | 5 | Sprint 1 | Anjali Waghmare | High | 03/20/2026 | 03/25/2026 | 5 | 19% | None | In Review | None | Notes for US-100

## Team Capacity
TEAM CAPACITY & RESOURCE ALLOCATION
Team Member | Role | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Total Points | Utilization % | Status
Sahil Betal | Tech Lead / Data Scientist | 45 | 35 | 40 | 45 | 50 | 215 | 100.0% | At Capacity
Anjali Waghmare | Data Engineer | 40 | 47 | 30 | 35 | 60 | 212 | 100.0% | At Capacity
Maithili Wagh | ML Engineer | 30 | 25 | 44 | 40 | 35 | 174 | 87.0% | Allocated
Vijay Ughade | Full Stack Developer | 35 | 40 | 35 | 51 | 40 | 201 | 100.0% | At Capacity
TOTAL |  | 150 | 147 | 149 | 171 | 185 | 802

## Daily Tasks
DAILY TASK BREAKDOWN - 15 DAY SPRINT
Day | Date | Task | Owner | Story ID | Hours | Priority | Status | Completed % | Notes
1 | 03/18 | Data exploration | Sahil Betal | US-077 | 4 | P3 | Done | 40% | Task details for Day 1
1 | 03/18 | Data cleaning | Anjali Waghmare | US-050 | 6 | P0 | In Progress | 18% | Task details for Day 1
1 | 03/18 | Feature engineering | Maithili Wagh | US-004 | 8 | P1 | Not Started | 0% | Task details for Day 1
1 | 03/18 | Model training | Vijay Ughade | US-058 | 6 | P3 | In Progress | 70% | Task details for Day 1
1 | 03/18 | Hyperparameter tuning | Sahil Betal | US-052 | 4 | P1 | In Progress | 99% | Task details for Day 1
1 | 03/18 | Visualization | Anjali Waghmare | US-100 | 4 | P1 | In Progress | 97% | Task details for Day 1
1 | 03/18 | Dashboard development | Maithili Wagh | US-065 | 2 | P1 | Not Started | 0% | Task details for Day 1
1 | 03/18 | Documentation | Vijay Ughade | US-027 | 4 | P2 | Not Started | 0% | Task details for Day 1
2 | 03/19 | Data exploration | Sahil Betal | US-017 | 2 | P0 | In Progress | 51% | Task details for Day 2
2 | 03/19 | Data cleaning | Anjali Waghmare | US-023 | 2 | P0 | Done | 25% | Task details for Day 2
2 | 03/19 | Feature engineering | Maithili Wagh | US-041 | 6 | P0 | In Progress | 89% | Task details for Day 2
2 | 03/19 | Model training | Vijay Ughade | US-010 | 8 | P2 | In Progress | 89% | Task details for Day 2
2 | 03/19 | Hyperparameter tuning | Sahil Betal | US-009 | 4 | P0 | In Progress | 2% | Task details for Day 2
2 | 03/19 | Visualization | Anjali Waghmare | US-060 | 8 | P0 | Done | 69% | Task details for Day 2
2 | 03/19 | Dashboard development | Maithili Wagh | US-078 | 2 | P0 | Not Started | 0% | Task details for Day 2
2 | 03/19 | Documentation | Vijay Ughade | US-064 | 2 | P1 | In Progress | 74% | Task details for Day 2
3 | 03/20 | Data exploration | Sahil Betal | US-031 | 4 | P3 | Not Started | 0% | Task details for Day 3
3 | 03/20 | Data cleaning | Anjali Waghmare | US-022 | 4 | P0 | Not Started | 0% | Task details for Day 3
3 | 03/20 | Feature engineering | Maithili Wagh | US-041 | 6 | P1 | Done | 31% | Task details for Day 3
3 | 03/20 | Model training | Vijay Ughade | US-017 | 6 | P2 | Done | 12% | Task details for Day 3
3 | 03/20 | Hyperparameter tuning | Sahil Betal | US-021 | 4 | P1 | Done | 30% | Task details for Day 3
3 | 03/20 | Visualization | Anjali Waghmare | US-020 | 2 | P0 | Done | 56% | Task details for Day 3
3 | 03/20 | Dashboard development | Maithili Wagh | US-070 | 4 | P1 | In Progress | 17% | Task details for Day 3
3 | 03/20 | Documentation | Vijay Ughade | US-001 | 4 | P3 | Done | 71% | Task details for Day 3
4 | 03/21 | Data exploration | Sahil Betal | US-031 | 2 | P0 | Not Started | 0% | Task details for Day 4
4 | 03/21 | Data cleaning | Anjali Waghmare | US-008 | 4 | P3 | Not Started | 0% | Task details for Day 4
4 | 03/21 | Feature engineering | Maithili Wagh | US-012 | 4 | P0 | Done | 11% | Task details for Day 4
4 | 03/21 | Model training | Vijay Ughade | US-049 | 8 | P0 | Not Started | 0% | Task details for Day 4
4 | 03/21 | Hyperparameter tuning | Sahil Betal | US-080 | 4 | P3 | Done | 41% | Task details for Day 4
4 | 03/21 | Visualization | Anjali Waghmare | US-078 | 2 | P0 | Not Started | 0% | Task details for Day 4
4 | 03/21 | Dashboard development | Maithili Wagh | US-020 | 2 | P3 | Done | 97% | Task details for Day 4
4 | 03/21 | Documentation | Vijay Ughade | US-010 | 6 | P0 | Done | 47% | Task details for Day 4
5 | 03/22 | Data exploration | Sahil Betal | US-053 | 6 | P3 | In Progress | 16% | Task details for Day 5
5 | 03/22 | Data cleaning | Anjali Waghmare | US-061 | 8 | P2 | Not Started | 0% | Task details for Day 5
5 | 03/22 | Feature engineering | Maithili Wagh | US-022 | 6 | P0 | Not Started | 0% | Task details for Day 5
5 | 03/22 | Model training | Vijay Ughade | US-026 | 8 | P2 | Done | 64% | Task details for Day 5
5 | 03/22 | Hyperparameter tuning | Sahil Betal | US-057 | 4 | P0 | Done | 46% | Task details for Day 5
5 | 03/22 | Visualization | Anjali Waghmare | US-015 | 8 | P1 | Done | 85% | Task details for Day 5
5 | 03/22 | Dashboard development | Maithili Wagh | US-059 | 6 | P2 | Not Started | 0% | Task details for Day 5
5 | 03/22 | Documentation | Vijay Ughade | US-019 | 6 | P3 | Done | 71% | Task details for Day 5
6 | 03/23 | Data exploration | Sahil Betal | US-074 | 8 | P3 | Done | 82% | Task details for Day 6
6 | 03/23 | Data cleaning | Anjali Waghmare | US-098 | 6 | P0 | Not Started | 0% | Task details for Day 6
6 | 03/23 | Feature engineering | Maithili Wagh | US-018 | 2 | P0 | Done | 16% | Task details for Day 6
6 | 03/23 | Model training | Vijay Ughade | US-052 | 6 | P1 | In Progress | 61% | Task details for Day 6
6 | 03/23 | Hyperparameter tuning | Sahil Betal | US-081 | 2 | P3 | Not Started | 0% | Task details for Day 6
6 | 03/23 | Visualization | Anjali Waghmare | US-005 | 8 | P1 | Done | 26% | Task details for Day 6
6 | 03/23 | Dashboard development | Maithili Wagh | US-065 | 6 | P3 | In Progress | 24% | Task details for Day 6
6 | 03/23 | Documentation | Vijay Ughade | US-022 | 8 | P2 | In Progress | 50% | Task details for Day 6
7 | 03/24 | Data exploration | Sahil Betal | US-011 | 4 | P1 | Done | 59% | Task details for Day 7
7 | 03/24 | Data cleaning | Anjali Waghmare | US-034 | 4 | P2 | Not Started | 0% | Task details for Day 7
7 | 03/24 | Feature engineering | Maithili Wagh | US-068 | 4 | P2 | In Progress | 71% | Task details for Day 7
7 | 03/24 | Model training | Vijay Ughade | US-022 | 8 | P0 | Not Started | 0% | Task details for Day 7
7 | 03/24 | Hyperparameter tuning | Sahil Betal | US-067 | 2 | P3 | Done | 15% | Task details for Day 7
7 | 03/24 | Visualization | Anjali Waghmare | US-037 | 2 | P0 | In Progress | 23% | Task details for Day 7
7 | 03/24 | Dashboard development | Maithili Wagh | US-008 | 2 | P1 | Done | 70% | Task details for Day 7
7 | 03/24 | Documentation | Vijay Ughade | US-037 | 2 | P0 | Not Started | 0% | Task details for Day 7
8 | 03/25 | Data exploration | Sahil Betal | US-084 | 2 | P0 | In Progress | 77% | Task details for Day 8
8 | 03/25 | Data cleaning | Anjali Waghmare | US-043 | 4 | P2 | Not Started | 0% | Task details for Day 8
8 | 03/25 | Feature engineering | Maithili Wagh | US-093 | 2 | P3 | In Progress | 45% | Task details for Day 8
8 | 03/25 | Model training | Vijay Ughade | US-100 | 2 | P3 | Done | 83% | Task details for Day 8
8 | 03/25 | Hyperparameter tuning | Sahil Betal | US-078 | 6 | P3 | Not Started | 0% | Task details for Day 8
8 | 03/25 | Visualization | Anjali Waghmare | US-060 | 4 | P2 | Done | 77% | Task details for Day 8
8 | 03/25 | Dashboard development | Maithili Wagh | US-031 | 2 | P1 | In Progress | 6% | Task details for Day 8
8 | 03/25 | Documentation | Vijay Ughade | US-085 | 8 | P3 | In Progress | 1% | Task details for Day 8
9 | 03/26 | Data exploration | Sahil Betal | US-015 | 4 | P1 | Done | 16% | Task details for Day 9
9 | 03/26 | Data cleaning | Anjali Waghmare | US-044 | 4 | P0 | Done | 99% | Task details for Day 9
9 | 03/26 | Feature engineering | Maithili Wagh | US-072 | 2 | P0 | Not Started | 0% | Task details for Day 9
9 | 03/26 | Model training | Vijay Ughade | US-027 | 2 | P0 | Not Started | 0% | Task details for Day 9
9 | 03/26 | Hyperparameter tuning | Sahil Betal | US-021 | 4 | P0 | Done | 70% | Task details for Day 9
9 | 03/26 | Visualization | Anjali Waghmare | US-029 | 6 | P2 | In Progress | 28% | Task details for Day 9
9 | 03/26 | Dashboard development | Maithili Wagh | US-019 | 4 | P2 | Not Started | 0% | Task details for Day 9
9 | 03/26 | Documentation | Vijay Ughade | US-096 | 8 | P2 | Not Started | 0% | Task details for Day 9
10 | 03/27 | Data exploration | Sahil Betal | US-081 | 8 | P1 | Done | 88% | Task details for Day 10
10 | 03/27 | Data cleaning | Anjali Waghmare | US-089 | 2 | P3 | Not Started | 0% | Task details for Day 10
10 | 03/27 | Feature engineering | Maithili Wagh | US-045 | 4 | P0 | In Progress | 26% | Task details for Day 10
10 | 03/27 | Model training | Vijay Ughade | US-096 | 2 | P2 | Not Started | 0% | Task details for Day 10
10 | 03/27 | Hyperparameter tuning | Sahil Betal | US-100 | 2 | P3 | Done | 22% | Task details for Day 10
10 | 03/27 | Visualization | Anjali Waghmare | US-078 | 8 | P2 | Done | 81% | Task details for Day 10
10 | 03/27 | Dashboard development | Maithili Wagh | US-001 | 6 | P3 | Done | 78% | Task details for Day 10
10 | 03/27 | Documentation | Vijay Ughade | US-029 | 8 | P0 | In Progress | 67% | Task details for Day 10
11 | 03/28 | Data exploration | Sahil Betal | US-021 | 8 | P2 | In Progress | 94% | Task details for Day 11
11 | 03/28 | Data cleaning | Anjali Waghmare | US-029 | 8 | P2 | Not Started | 0% | Task details for Day 11
11 | 03/28 | Feature engineering | Maithili Wagh | US-034 | 2 | P3 | In Progress | 81% | Task details for Day 11
11 | 03/28 | Model training | Vijay Ughade | US-002 | 4 | P3 | In Progress | 22% | Task details for Day 11
11 | 03/28 | Hyperparameter tuning | Sahil Betal | US-071 | 8 | P2 | In Progress | 10% | Task details for Day 11
11 | 03/28 | Visualization | Anjali Waghmare | US-058 | 8 | P2 | Done | 90% | Task details for Day 11
11 | 03/28 | Dashboard development | Maithili Wagh | US-051 | 8 | P3 | In Progress | 19% | Task details for Day 11
11 | 03/28 | Documentation | Vijay Ughade | US-083 | 2 | P3 | Done | 31% | Task details for Day 11
12 | 03/29 | Data exploration | Sahil Betal | US-035 | 2 | P1 | Done | 12% | Task details for Day 12
12 | 03/29 | Data cleaning | Anjali Waghmare | US-043 | 4 | P1 | Not Started | 0% | Task details for Day 12
12 | 03/29 | Feature engineering | Maithili Wagh | US-050 | 4 | P1 | In Progress | 35% | Task details for Day 12
12 | 03/29 | Model training | Vijay Ughade | US-059 | 8 | P3 | Not Started | 0% | Task details for Day 12
12 | 03/29 | Hyperparameter tuning | Sahil Betal | US-083 | 2 | P1 | In Progress | 75% | Task details for Day 12
12 | 03/29 | Visualization | Anjali Waghmare | US-002 | 4 | P3 | Not Started | 0% | Task details for Day 12
12 | 03/29 | Dashboard development | Maithili Wagh | US-080 | 4 | P2 | Done | 26% | Task details for Day 12
12 | 03/29 | Documentation | Vijay Ughade | US-043 | 4 | P0 | Done | 2% | Task details for Day 12
13 | 03/30 | Data exploration | Sahil Betal | US-037 | 2 | P1 | Done | 54% | Task details for Day 13
13 | 03/30 | Data cleaning | Anjali Waghmare | US-088 | 6 | P0 | Not Started | 0% | Task details for Day 13
13 | 03/30 | Feature engineering | Maithili Wagh | US-059 | 4 | P2 | Not Started | 0% | Task details for Day 13
13 | 03/30 | Model training | Vijay Ughade | US-020 | 6 | P2 | Not Started | 0% | Task details for Day 13
13 | 03/30 | Hyperparameter tuning | Sahil Betal | US-031 | 6 | P0 | In Progress | 68% | Task details for Day 13
13 | 03/30 | Visualization | Anjali Waghmare | US-057 | 4 | P1 | Done | 93% | Task details for Day 13
13 | 03/30 | Dashboard development | Maithili Wagh | US-047 | 6 | P2 | In Progress | 10% | Task details for Day 13
13 | 03/30 | Documentation | Vijay Ughade | US-089 | 2 | P1 | Not Started | 0% | Task details for Day 13
14 | 03/31 | Data exploration | Sahil Betal | US-088 | 2 | P2 | Done | 57% | Task details for Day 14
14 | 03/31 | Data cleaning | Anjali Waghmare | US-081 | 8 | P1 | Done | 79% | Task details for Day 14
14 | 03/31 | Feature engineering | Maithili Wagh | US-070 | 8 | P1 | In Progress | 97% | Task details for Day 14
14 | 03/31 | Model training | Vijay Ughade | US-009 | 4 | P0 | Done | 31% | Task details for Day 14
14 | 03/31 | Hyperparameter tuning | Sahil Betal | US-024 | 8 | P1 | In Progress | 72% | Task details for Day 14
14 | 03/31 | Visualization | Anjali Waghmare | US-051 | 4 | P0 | Done | 42% | Task details for Day 14
14 | 03/31 | Dashboard development | Maithili Wagh | US-048 | 6 | P2 | Done | 80% | Task details for Day 14
14 | 03/31 | Documentation | Vijay Ughade | US-011 | 4 | P0 | In Progress | 23% | Task details for Day 14
15 | 04/01 | Data exploration | Sahil Betal | US-013 | 4 | P1 | Not Started | 0% | Task details for Day 15
15 | 04/01 | Data cleaning | Anjali Waghmare | US-071 | 6 | P0 | Not Started | 0% | Task details for Day 15
15 | 04/01 | Feature engineering | Maithili Wagh | US-094 | 4 | P2 | In Progress | 74% | Task details for Day 15
15 | 04/01 | Model training | Vijay Ughade | US-065 | 8 | P1 | In Progress | 96% | Task details for Day 15
15 | 04/01 | Hyperparameter tuning | Sahil Betal | US-050 | 4 | P2 | Done | 71% | Task details for Day 15
15 | 04/01 | Visualization | Anjali Waghmare | US-061 | 2 | P2 | Not Started | 0% | Task details for Day 15
15 | 04/01 | Dashboard development | Maithili Wagh | US-061 | 6 | P0 | Done | 7% | Task details for Day 15
15 | 04/01 | Documentation | Vijay Ughade | US-040 | 4 | P0 | Not Started | 0% | Task details for Day 15

## Burndown Data
SPRINT 1
Day | Planned Points | Completed Points | Remaining Points | Velocity | Team Capacity | Notes
Day 1 | 45 | 15 | 30 | 15.0 | 40 hrs | Burndown for Sprint 1 Day 1
Day 2 | 45 | 27 | 18 | 13.5 | 40 hrs | Burndown for Sprint 1 Day 2
Day 3 | 45 | 45 | 0 | 15.0 | 40 hrs | Burndown for Sprint 1 Day 3
SPRINT 2
Day | Planned Points | Completed Points | Remaining Points | Velocity | Team Capacity | Notes
Day 1 | 47 | 13 | 34 | 13.0 | 40 hrs | Burndown for Sprint 2 Day 1
Day 2 | 47 | 33 | 14 | 16.5 | 40 hrs | Burndown for Sprint 2 Day 2
Day 3 | 47 | 48 | 0 | 16.0 | 40 hrs | Burndown for Sprint 2 Day 3
SPRINT 3
Day | Planned Points | Completed Points | Remaining Points | Velocity | Team Capacity | Notes
Day 1 | 44 | 15 | 29 | 15.0 | 40 hrs | Burndown for Sprint 3 Day 1
Day 2 | 44 | 29 | 15 | 14.5 | 40 hrs | Burndown for Sprint 3 Day 2
Day 3 | 44 | 41 | 3 | 13.7 | 40 hrs | Burndown for Sprint 3 Day 3
SPRINT 4
Day | Planned Points | Completed Points | Remaining Points | Velocity | Team Capacity | Notes
Day 1 | 51 | 13 | 38 | 13.0 | 40 hrs | Burndown for Sprint 4 Day 1
Day 2 | 51 | 32 | 19 | 16.0 | 40 hrs | Burndown for Sprint 4 Day 2
Day 3 | 51 | 45 | 6 | 15.0 | 40 hrs | Burndown for Sprint 4 Day 3
SPRINT 5
Day | Planned Points | Completed Points | Remaining Points | Velocity | Team Capacity | Notes
Day 1 | 68 | 18 | 50 | 18.0 | 40 hrs | Burndown for Sprint 5 Day 1
Day 2 | 68 | 42 | 26 | 21.0 | 40 hrs | Burndown for Sprint 5 Day 2
Day 3 | 68 | 57 | 11 | 19.0 | 40 hrs | Burndown for Sprint 5 Day 3

## Priority Matrix
PRIORITY × IMPACT MATRIX
P0 Critical | P0 High | P0 Medium | P0 Low | P0 Minimal | P1 Critical | P1 High | P1 Medium | P1 Low | P1 Minimal | P2 Critical | P2 High | P2 Medium | P2 Low | P2 Minimal | P3 Critical | P3 High | P3 Medium | P3 Low | P3 Minimal
US-042 (3pts) | US-051 (5pts) | US-039 (8pts) | US-063 (13pts) | US-057 (3pts) | US-039 (5pts) | US-091 (8pts) | US-100 (21pts) | US-093 (8pts) | US-060 (21pts) | US-087 (3pts) | US-033 (8pts) | US-067 (21pts) | US-051 (3pts) | US-074 (8pts) | US-025 (13pts) | US-027 (13pts) | US-019 (3pts) | US-100 (3pts) | US-028 (5pts)
US-079 (3pts) | US-073 (8pts) | US-026 (5pts) | US-030 (13pts) | US-094 (21pts) | US-052 (5pts) | US-010 (3pts) | US-019 (5pts) | US-020 (21pts) | US-076 (3pts) | US-084 (8pts) | US-052 (21pts) | US-052 (13pts) | US-042 (5pts) | US-093 (3pts) | US-020 (13pts) | US-040 (3pts) | US-090 (13pts) | US-075 (3pts) | US-009 (3pts)
US-053 (3pts) | US-019 (5pts) | US-086 (13pts) | US-074 (21pts) | US-056 (5pts) | US-006 (21pts) | US-046 (13pts) | US-096 (3pts) | US-013 (8pts) | US-033 (8pts) | US-059 (8pts) | US-087 (5pts) | US-048 (8pts) | US-039 (8pts) | US-097 (21pts) | US-039 (5pts) | US-023 (13pts) | US-023 (8pts) | US-031 (5pts) | US-041 (13pts)
US-069 (13pts) | US-057 (21pts) | US-083 (5pts) | US-080 (3pts) | US-068 (5pts) | US-063 (8pts) | US-050 (8pts) | US-052 (13pts) | US-074 (3pts) | US-085 (8pts) | US-065 (21pts) | US-030 (8pts) | US-086 (3pts) | US-083 (5pts) | US-004 (5pts) | US-066 (21pts) | US-034 (13pts) | US-042 (3pts) | US-027 (3pts) | US-025 (13pts)
US-048 (5pts) | US-015 (13pts) | US-048 (5pts) | US-048 (13pts) | US-057 (21pts) | US-036 (5pts) | US-073 (3pts) | US-098 (5pts) | US-096 (21pts) | US-099 (8pts) | US-033 (13pts) | US-062 (3pts) | US-013 (21pts) | US-066 (21pts) | US-002 (21pts) | US-005 (8pts) | US-077 (8pts) | US-085 (3pts) | US-022 (13pts) | US-097 (3pts)
US-075 (21pts) | US-078 (3pts) | US-066 (8pts) | US-013 (21pts) | US-011 (13pts) | US-003 (13pts) | US-073 (13pts) | US-037 (21pts) | US-045 (8pts) | US-039 (8pts) | US-071 (8pts) | US-046 (13pts) | US-082 (3pts) | US-050 (21pts) | US-035 (21pts) | US-091 (3pts) | US-035 (5pts) | US-099 (21pts) | US-091 (5pts) | US-024 (5pts)
US-078 (3pts) | US-059 (5pts) | US-096 (21pts) | US-039 (5pts) | US-057 (5pts) | US-003 (5pts) | US-086 (8pts) | US-016 (13pts) | US-083 (5pts) | US-014 (13pts) | US-077 (5pts) | US-087 (13pts) | US-096 (3pts) | US-039 (3pts) | US-034 (5pts) | US-017 (5pts) | US-016 (21pts) | US-001 (3pts) | US-040 (8pts) | US-077 (3pts)
US-078 (8pts) | US-025 (13pts) | US-021 (8pts) | US-040 (8pts) | US-012 (13pts) | US-019 (8pts) | US-007 (3pts) | US-001 (5pts) | US-069 (5pts) | US-052 (5pts) | US-035 (8pts) | US-087 (3pts) | US-094 (13pts) | US-065 (3pts) | US-053 (3pts) | US-005 (21pts) | US-058 (3pts) | US-060 (8pts) | US-093 (8pts) | US-030 (3pts)
US-041 (13pts) | US-044 (21pts) | US-077 (13pts) | US-021 (5pts) | US-040 (8pts) | US-034 (21pts) | US-009 (8pts) | US-080 (3pts) | US-011 (8pts) | US-015 (5pts) | US-039 (8pts) | US-053 (13pts) | US-022 (3pts) | US-001 (3pts) | US-030 (21pts) | US-088 (13pts) | US-017 (13pts) | US-099 (13pts) | US-086 (5pts) | US-056 (3pts)
US-016 (13pts) | US-011 (5pts) | US-038 (3pts) | US-026 (8pts) | US-004 (13pts) | US-078 (8pts) | US-077 (5pts) | US-011 (21pts) | US-076 (3pts) | US-042 (3pts) | US-029 (8pts) | US-005 (5pts) | US-053 (21pts) | US-042 (5pts) | US-051 (21pts) | US-044 (3pts) | US-064 (3pts) | US-009 (3pts) | US-028 (21pts) | US-054 (3pts)
US-096 (5pts) | US-035 (5pts) | US-008 (13pts) | US-043 (5pts) | US-083 (5pts) | US-035 (8pts) | US-082 (5pts) | US-019 (3pts) | US-004 (21pts) | US-089 (21pts) | US-036 (5pts) | US-038 (3pts) | US-034 (13pts) | US-033 (13pts) | US-027 (5pts) | US-075 (8pts) | US-034 (8pts) | US-055 (3pts) | US-091 (3pts) | US-083 (8pts)
US-060 (5pts) | US-095 (3pts) | US-010 (13pts) | US-082 (21pts) | US-097 (5pts) | US-085 (13pts) | US-056 (13pts) | US-043 (8pts) | US-100 (13pts) | US-027 (3pts) | US-069 (5pts) | US-085 (3pts) | US-064 (21pts) | US-028 (21pts) | US-063 (8pts) | US-017 (3pts) | US-068 (5pts) | US-077 (8pts) | US-067 (13pts) | US-062 (3pts)
US-008 (5pts) | US-033 (3pts) | US-028 (21pts) | US-041 (21pts) | US-009 (5pts) | US-082 (3pts) | US-031 (3pts) | US-063 (21pts) | US-048 (21pts) | US-078 (5pts) | US-045 (8pts) | US-076 (13pts) | US-054 (13pts) | US-034 (5pts) | US-076 (5pts) | US-022 (5pts) | US-005 (8pts) | US-089 (21pts) | US-045 (8pts) | US-042 (8pts)
US-033 (5pts) | US-045 (3pts) | US-094 (5pts) | US-037 (21pts) | US-090 (21pts) | US-047 (8pts) | US-068 (5pts) | US-030 (5pts) | US-001 (8pts) | US-006 (21pts) | US-095 (8pts) | US-048 (21pts) | US-019 (5pts) | US-056 (21pts) | US-044 (3pts) | US-007 (21pts) | US-050 (13pts) | US-076 (3pts) | US-042 (13pts) | US-011 (13pts)
US-088 (21pts) | US-070 (3pts) | US-052 (5pts) | US-010 (5pts) | US-056 (21pts) | US-006 (5pts) | US-038 (3pts) | US-087 (5pts) | US-077 (13pts) | US-087 (5pts) | US-013 (21pts) | US-008 (3pts) | US-004 (8pts) | US-033 (5pts) | US-024 (21pts) | US-097 (5pts) | US-035 (5pts) | US-091 (13pts) | US-025 (8pts) | US-028 (5pts)
US-025 (3pts) | US-088 (5pts) | US-089 (5pts) | US-049 (13pts) | US-039 (3pts) | US-032 (8pts) | US-088 (3pts) | US-068 (21pts) | US-046 (5pts) | US-075 (21pts) | US-058 (13pts) | US-049 (3pts) | US-024 (3pts) | US-009 (3pts) | US-018 (3pts) | US-092 (8pts) | US-075 (8pts) | US-043 (3pts) | US-048 (3pts) | US-090 (21pts)
US-070 (21pts) | US-019 (21pts) | US-070 (5pts) | US-079 (13pts) | US-002 (3pts) | US-012 (13pts) | US-007 (21pts) | US-036 (13pts) | US-028 (8pts) | US-049 (5pts) | US-043 (8pts) | US-015 (8pts) | US-064 (3pts) | US-013 (13pts) | US-094 (5pts) | US-092 (5pts) | US-085 (21pts) | US-070 (8pts) | US-093 (3pts) | US-066 (21pts)
US-010 (3pts) | US-077 (3pts) | US-085 (5pts) | US-039 (3pts) | US-053 (5pts) | US-087 (5pts) | US-029 (3pts) | US-068 (13pts) | US-044 (13pts) | US-068 (21pts) | US-095 (8pts) | US-100 (3pts) | US-055 (13pts) | US-049 (5pts) | US-100 (5pts) | US-098 (21pts) | US-056 (13pts) | US-088 (3pts) | US-060 (21pts) | US-007 (8pts)
US-074 (5pts) | US-073 (3pts) | US-075 (3pts) | US-004 (8pts) | US-014 (5pts) | US-098 (13pts) | US-036 (3pts) | US-097 (8pts) | US-074 (13pts) | US-022 (5pts) | US-077 (13pts) | US-010 (8pts) | US-046 (8pts) | US-042 (8pts) | US-001 (5pts) | US-018 (8pts) | US-006 (21pts) | US-033 (21pts) | US-033 (13pts) | US-085 (5pts)
US-023 (13pts) | US-054 (21pts) | US-098 (5pts) | US-062 (21pts) | US-070 (5pts) | US-079 (13pts) | US-064 (5pts) | US-079 (5pts) | US-046 (5pts) | US-084 (5pts) | US-008 (13pts) | US-085 (5pts) | US-027 (21pts) | US-062 (3pts) | US-080 (21pts) | US-073 (8pts) | US-011 (21pts) | US-068 (21pts) | US-069 (21pts) | US-047 (5pts)
US-055 (13pts) | US-008 (21pts) | US-040 (13pts) | US-029 (13pts) | US-084 (21pts) | US-030 (21pts) | US-018 (13pts) | US-081 (13pts) | US-065 (21pts) | US-074 (13pts) | US-053 (21pts) | US-054 (3pts) | US-086 (5pts) | US-070 (21pts) | US-059 (5pts) | US-007 (3pts) | US-038 (21pts) | US-090 (8pts) | US-063 (21pts) | US-030 (5pts)
US-056 (13pts) | US-008 (21pts) | US-032 (21pts) | US-002 (8pts) | US-058 (3pts) | US-050 (3pts) | US-080 (3pts) | US-043 (21pts) | US-054 (3pts) | US-024 (8pts) | US-032 (8pts) | US-062 (21pts) | US-089 (3pts) | US-036 (5pts) | US-001 (21pts) | US-059 (5pts) | US-020 (13pts) | US-085 (13pts) | US-061 (21pts) | US-078 (8pts)
US-058 (8pts) | US-058 (5pts) | US-089 (21pts) | US-093 (8pts) | US-044 (5pts) | US-003 (8pts) | US-097 (3pts) | US-073 (5pts) | US-014 (8pts) | US-097 (3pts) | US-078 (8pts) | US-010 (13pts) | US-010 (13pts) | US-012 (21pts) | US-026 (13pts) | US-026 (3pts) | US-074 (13pts) | US-042 (13pts) | US-057 (3pts) | US-094 (5pts)
US-091 (21pts) | US-049 (5pts) | US-070 (8pts) | US-061 (21pts) | US-003 (21pts) | US-031 (5pts) | US-066 (8pts) | US-021 (5pts) | US-055 (13pts) | US-024 (3pts) | US-065 (3pts) | US-070 (21pts) | US-088 (21pts) | US-092 (8pts) | US-043 (5pts) | US-100 (3pts) | US-042 (21pts) | US-038 (5pts) | US-034 (8pts) | US-018 (3pts)
US-059 (5pts) | US-057 (8pts) | US-050 (21pts) | US-051 (3pts) | US-091 (21pts) | US-065 (5pts) | US-019 (5pts) | US-097 (5pts) | US-058 (3pts) | US-011 (5pts) | US-024 (21pts) | US-056 (5pts) | US-083 (5pts) | US-032 (21pts) | US-099 (3pts) | US-062 (5pts) | US-041 (13pts) | US-044 (5pts) | US-087 (5pts) | US-021 (3pts)
US-076 (13pts) | US-021 (5pts) | US-088 (5pts) | US-020 (13pts) | US-100 (5pts) | US-051 (8pts) | US-040 (5pts) | US-031 (3pts) | US-093 (5pts) | US-067 (5pts) | US-096 (5pts) | US-014 (13pts) | US-010 (5pts) | US-054 (3pts) | US-091 (5pts) | US-056 (21pts) | US-045 (8pts) | US-085 (8pts) | US-061 (8pts) | US-033 (21pts)
US-075 (5pts) | US-010 (5pts) | US-065 (8pts) | US-014 (3pts) | US-044 (5pts) | US-064 (5pts) | US-098 (5pts) | US-067 (13pts) | US-016 (5pts) | US-009 (8pts) | US-051 (3pts) | US-036 (13pts) | US-012 (5pts) | US-011 (21pts) | US-034 (8pts) | US-066 (8pts) | US-050 (5pts) | US-006 (21pts) | US-029 (5pts) | US-048 (5pts)
US-036 (13pts) | US-024 (8pts) | US-078 (13pts) | US-021 (3pts) | US-013 (21pts) | US-031 (5pts) | US-032 (3pts) | US-087 (13pts) | US-059 (13pts) | US-017 (3pts) | US-053 (3pts) | US-018 (5pts) | US-030 (8pts) | US-077 (8pts) | US-003 (13pts) | US-027 (5pts) | US-029 (5pts) | US-069 (8pts) | US-047 (5pts) | US-016 (21pts)
US-021 (13pts) | US-086 (3pts) | US-036 (3pts) | US-058 (5pts) | US-096 (13pts) | US-045 (5pts) | US-023 (13pts) | US-050 (13pts) | US-062 (5pts) | US-017 (3pts) | US-038 (13pts) | US-080 (3pts) | US-011 (21pts) | US-039 (13pts) | US-067 (13pts) | US-031 (13pts) | US-032 (3pts) | US-094 (8pts) | US-094 (8pts) | US-074 (3pts)
US-067 (21pts) | US-049 (8pts) | US-006 (13pts) | US-084 (13pts) | US-043 (5pts) | US-005 (8pts) | US-033 (5pts) | US-082 (8pts) | US-031 (21pts) | US-100 (5pts) | US-046 (5pts) | US-054 (3pts) | US-089 (21pts) | US-068 (21pts) | US-084 (3pts) | US-078 (5pts) | US-076 (21pts) | US-010 (8pts) | US-036 (13pts) | US-027 (13pts)
US-040 (8pts) | US-074 (13pts) | US-033 (5pts) | US-025 (5pts) | US-059 (5pts) | US-042 (3pts) | US-098 (21pts) | US-091 (3pts) | US-083 (13pts) | US-051 (13pts) | US-033 (13pts) | US-004 (13pts) | US-039 (8pts) | US-054 (13pts) | US-062 (21pts) | US-020 (5pts) | US-065 (5pts) | US-067 (5pts) | US-078 (3pts) | US-037 (5pts)
US-053 (3pts) | US-057 (8pts) | US-041 (21pts) | US-029 (21pts) | US-035 (5pts) | US-083 (5pts) | US-027 (13pts) | US-013 (13pts) | US-095 (8pts) | US-060 (3pts) | US-034 (3pts) | US-011 (3pts) | US-099 (21pts) | US-033 (21pts) | US-068 (3pts) | US-100 (21pts) | US-061 (21pts) | US-065 (3pts) | US-041 (8pts) | US-008 (8pts)
US-016 (8pts) | US-004 (13pts) | US-078 (21pts) | US-025 (13pts) | US-084 (21pts) | US-067 (21pts) | US-097 (21pts) | US-064 (3pts) | US-064 (8pts) | US-090 (8pts) | US-072 (5pts) | US-057 (13pts) | US-002 (5pts) | US-005 (13pts) | US-049 (13pts) | US-076 (8pts) | US-010 (21pts) | US-063 (5pts) | US-031 (21pts) | US-099 (13pts)
US-095 (21pts) | US-059 (3pts) | US-038 (8pts) | US-081 (21pts) | US-005 (13pts) | US-091 (5pts) | US-069 (21pts) | US-086 (3pts) | US-017 (13pts) | US-026 (5pts) | US-009 (13pts) | US-044 (21pts) | US-020 (5pts) | US-070 (8pts) | US-050 (3pts) | US-048 (5pts) | US-091 (21pts) | US-076 (8pts) | US-031 (13pts) | US-094 (8pts)
US-027 (13pts) | US-005 (3pts) | US-074 (5pts) | US-008 (13pts) | US-053 (13pts) | US-045 (8pts) | US-082 (3pts) | US-036 (21pts) | US-083 (3pts) | US-100 (13pts) | US-098 (8pts) | US-018 (5pts) | US-052 (8pts) | US-047 (13pts) | US-018 (21pts) | US-066 (5pts) | US-093 (5pts) | US-004 (5pts) | US-095 (21pts) | US-047 (3pts)
US-038 (3pts) | US-065 (5pts) | US-050 (3pts) | US-068 (21pts) | US-069 (5pts) | US-083 (8pts) | US-056 (8pts) | US-065 (13pts) | US-069 (13pts) | US-069 (13pts) | US-094 (3pts) | US-056 (13pts) | US-083 (21pts) | US-031 (21pts) | US-007 (8pts) | US-074 (13pts) | US-002 (21pts) | US-081 (8pts) | US-002 (5pts) | US-017 (21pts)
US-064 (3pts) | US-047 (3pts) | US-020 (3pts) | US-088 (13pts) | US-024 (3pts) | US-001 (13pts) | US-054 (5pts) | US-065 (13pts) | US-066 (13pts) | US-070 (3pts) | US-038 (3pts) | US-081 (5pts) | US-062 (21pts) | US-082 (5pts) | US-016 (13pts) | US-038 (13pts) | US-017 (21pts) | US-030 (3pts) | US-043 (21pts) | US-038 (13pts)
US-095 (13pts) | US-051 (3pts) | US-034 (3pts) | US-038 (8pts) | US-061 (21pts) | US-007 (21pts) | US-081 (5pts) | US-070 (21pts) | US-053 (3pts) | US-032 (13pts) | US-078 (3pts) | US-011 (5pts) | US-018 (5pts) | US-081 (21pts) | US-068 (21pts) | US-061 (21pts) | US-019 (3pts) | US-032 (13pts) | US-025 (8pts) | US-021 (3pts)
US-064 (21pts) | US-001 (8pts) | US-045 (5pts) | US-037 (13pts) | US-047 (13pts) | US-078 (3pts) | US-063 (3pts) | US-083 (3pts) | US-095 (13pts) | US-019 (5pts) | US-086 (8pts) | US-087 (21pts) | US-049 (8pts) | US-091 (5pts) | US-003 (3pts) | US-028 (8pts) | US-045 (13pts) | US-021 (3pts) | US-061 (5pts) | US-084 (5pts)
US-031 (13pts) | US-095 (8pts) | US-002 (21pts) | US-099 (3pts) | US-041 (8pts) | US-035 (13pts) | US-052 (13pts) | US-033 (13pts) | US-031 (8pts) | US-098 (3pts) | US-084 (3pts) | US-080 (3pts) | US-022 (3pts) | US-026 (3pts) | US-025 (8pts) | US-031 (13pts) | US-056 (13pts) | US-057 (13pts) | US-038 (13pts) | US-093 (13pts)
US-050 (5pts) | US-027 (21pts) | US-035 (3pts) | US-010 (21pts) | US-044 (5pts) | US-051 (5pts) | US-027 (13pts) | US-050 (3pts) | US-020 (3pts) | US-040 (3pts) | US-004 (8pts) | US-038 (21pts) | US-002 (5pts) | US-041 (8pts) | US-043 (13pts) | US-006 (8pts) | US-015 (13pts) | US-100 (5pts) | US-004 (8pts) | US-066 (13pts)
US-098 (21pts) | US-088 (3pts) | US-096 (13pts) | US-016 (13pts) | US-024 (21pts) | US-004 (21pts) | US-041 (5pts) | US-003 (8pts) | US-017 (13pts) | US-069 (21pts) | US-079 (21pts) | US-021 (13pts) | US-085 (13pts) | US-013 (8pts) | US-015 (13pts) | US-001 (3pts) | US-039 (5pts) | US-066 (5pts) | US-073 (8pts) | US-036 (8pts)
US-023 (13pts) | US-063 (13pts) | US-061 (21pts) | US-003 (13pts) | US-067 (3pts) | US-054 (21pts) | US-004 (5pts) | US-025 (8pts) | US-089 (8pts) | US-076 (13pts) | US-031 (3pts) | US-011 (5pts) | US-020 (21pts) | US-076 (3pts) | US-055 (21pts) | US-075 (13pts) | US-082 (21pts) | US-013 (8pts) | US-077 (8pts) | US-034 (21pts)
US-029 (5pts) | US-095 (13pts) | US-026 (13pts) | US-094 (13pts) | US-052 (5pts) | US-049 (21pts) | US-095 (13pts) | US-022 (8pts) | US-073 (8pts) | US-008 (5pts) | US-072 (21pts) | US-049 (5pts) | US-072 (13pts) | US-095 (13pts) | US-034 (21pts) | US-081 (8pts) | US-061 (21pts) | US-021 (13pts) | US-052 (21pts) | US-066 (3pts)
US-078 (5pts) | US-017 (5pts) | US-049 (21pts) | US-071 (21pts) | US-081 (5pts) | US-087 (3pts) | US-076 (5pts) | US-100 (3pts) | US-008 (21pts) | US-019 (13pts) | US-062 (8pts) | US-047 (13pts) | US-024 (3pts) | US-092 (13pts) | US-078 (3pts) | US-006 (21pts) | US-072 (5pts) | US-052 (13pts) | US-087 (5pts) | US-084 (13pts)
US-031 (13pts) | US-077 (13pts) | US-017 (13pts) | US-096 (8pts) | US-032 (3pts) | US-039 (5pts) | US-045 (5pts) | US-055 (5pts) | US-049 (3pts) | US-093 (8pts) | US-048 (3pts) | US-054 (8pts) | US-054 (21pts) | US-025 (21pts) | US-012 (8pts) | US-045 (8pts) | US-072 (8pts) | US-037 (8pts) | US-010 (3pts) | US-035 (21pts)
US-094 (21pts) | US-056 (5pts) | US-052 (3pts) | US-032 (21pts) | US-034 (8pts) | US-018 (21pts) | US-091 (13pts) | US-099 (3pts) | US-058 (21pts) | US-067 (13pts) | US-081 (3pts) | US-079 (8pts) | US-048 (13pts) | US-016 (13pts) | US-026 (5pts) | US-003 (3pts) | US-053 (3pts) | US-021 (8pts) | US-069 (13pts) | US-013 (3pts)
US-027 (5pts) | US-063 (13pts) | US-071 (5pts) | US-088 (8pts) | US-033 (21pts) | US-045 (5pts) | US-061 (21pts) | US-082 (13pts) | US-060 (21pts) | US-004 (5pts) | US-013 (13pts) | US-010 (21pts) | US-069 (5pts) | US-029 (8pts) | US-020 (5pts) | US-047 (3pts) | US-043 (5pts) | US-004 (8pts) | US-070 (21pts) | US-073 (13pts)
US-059 (3pts) | US-020 (21pts) | US-098 (13pts) | US-062 (3pts) | US-080 (13pts) | US-055 (3pts) | US-030 (21pts) | US-043 (8pts) | US-032 (21pts) | US-067 (8pts) | US-010 (3pts) | US-046 (13pts) | US-071 (8pts) | US-027 (3pts) | US-009 (13pts) | US-083 (8pts) | US-016 (13pts) | US-071 (5pts) | US-043 (21pts) | US-088 (21pts)
US-083 (13pts) | US-006 (13pts) | US-037 (5pts) | US-030 (5pts) | US-009 (13pts) | US-097 (13pts) | US-097 (21pts) | US-011 (8pts) | US-084 (13pts) | US-086 (8pts) | US-059 (5pts) | US-085 (8pts) | US-033 (5pts) | US-087 (13pts) | US-035 (5pts) | US-072 (13pts) | US-026 (13pts) | US-100 (21pts) | US-032 (5pts) | US-017 (8pts)
US-043 (3pts) | US-048 (21pts) | US-065 (8pts) | US-096 (8pts) | US-071 (3pts) | US-038 (8pts) | US-090 (8pts) | US-092 (8pts) | US-011 (21pts) | US-083 (21pts) | US-029 (21pts) | US-079 (5pts) | US-043 (3pts) | US-014 (3pts) | US-084 (3pts) | US-081 (13pts) | US-021 (3pts) | US-085 (13pts) | US-042 (13pts) | US-071 (3pts)
US-024 (8pts) | US-008 (21pts) | US-015 (21pts) | US-086 (8pts) | US-051 (13pts) | US-073 (5pts) | US-029 (3pts) | US-068 (8pts) | US-084 (3pts) | US-005 (5pts) | US-073 (13pts) | US-054 (13pts) | US-005 (5pts) | US-092 (8pts) | US-012 (8pts) | US-047 (21pts) | US-071 (3pts) | US-020 (8pts) | US-094 (5pts) | US-080 (13pts)
US-092 (5pts) | US-028 (21pts) | US-013 (5pts) | US-051 (8pts) | US-035 (5pts) | US-032 (13pts) | US-047 (13pts) | US-026 (8pts) | US-015 (5pts) | US-100 (13pts) | US-015 (13pts) | US-065 (5pts) | US-087 (21pts) | US-045 (3pts) | US-010 (13pts) | US-093 (5pts) | US-090 (5pts) | US-087 (21pts) | US-084 (13pts) | US-018 (13pts)
US-023 (13pts) | US-070 (8pts) | US-048 (21pts) | US-081 (5pts) | US-063 (13pts) | US-072 (5pts) | US-029 (13pts) | US-088 (13pts) | US-099 (3pts) | US-093 (3pts) | US-028 (8pts) | US-064 (13pts) | US-057 (3pts) | US-051 (21pts) | US-090 (13pts) | US-028 (13pts) | US-079 (5pts) | US-081 (21pts) | US-013 (13pts) | US-055 (5pts)
US-032 (5pts) | US-092 (8pts) | US-045 (8pts) | US-030 (21pts) | US-091 (5pts) | US-042 (5pts) | US-042 (13pts) | US-056 (3pts) | US-036 (13pts) | US-018 (13pts) | US-046 (8pts) | US-075 (5pts) | US-072 (21pts) | US-099 (13pts) | US-022 (8pts) | US-029 (21pts) | US-015 (8pts) | US-004 (13pts) | US-075 (21pts) | US-037 (21pts)
US-083 (3pts) | US-043 (21pts) | US-076 (21pts) | US-031 (8pts) | US-071 (5pts) | US-097 (13pts) | US-085 (3pts) | US-015 (21pts) | US-037 (13pts) | US-034 (5pts) | US-043 (3pts) | US-010 (13pts) | US-038 (3pts) | US-064 (3pts) | US-037 (3pts) | US-049 (8pts) | US-028 (13pts) | US-080 (21pts) | US-015 (13pts) | US-088 (13pts)
US-019 (3pts) | US-081 (8pts) | US-091 (8pts) | US-028 (3pts) | US-084 (8pts) | US-014 (21pts) | US-009 (8pts) | US-044 (3pts) | US-027 (5pts) | US-097 (5pts) | US-087 (5pts) | US-074 (3pts) | US-009 (21pts) | US-073 (3pts) | US-070 (21pts) | US-059 (3pts) | US-005 (21pts) | US-099 (8pts) | US-048 (21pts) | US-079 (13pts)
US-029 (3pts) | US-024 (5pts) | US-057 (8pts) | US-086 (8pts) | US-015 (3pts) | US-038 (21pts) | US-053 (5pts) | US-014 (5pts) | US-027 (8pts) | US-065 (3pts) | US-052 (5pts) | US-049 (5pts) | US-088 (21pts) | US-094 (13pts) | US-031 (3pts) | US-066 (3pts) | US-070 (8pts) | US-018 (13pts) | US-049 (3pts) | US-068 (5pts)
US-056 (3pts) | US-018 (5pts) | US-007 (21pts) | US-080 (3pts) | US-096 (21pts) | US-070 (5pts) | US-021 (8pts) | US-028 (5pts) | US-073 (3pts) | US-085 (8pts) | US-016 (21pts) | US-084 (13pts) | US-074 (5pts) | US-003 (5pts) | US-021 (13pts) | US-030 (5pts) | US-060 (21pts) | US-062 (13pts) | US-048 (13pts) | US-091 (21pts)
US-020 (21pts) | US-032 (5pts) | US-001 (3pts) | US-047 (3pts) | US-078 (3pts) | US-071 (13pts) | US-098 (13pts) | US-040 (8pts) | US-016 (13pts) | US-013 (8pts) | US-003 (8pts) | US-010 (5pts) | US-005 (13pts) | US-002 (8pts) | US-015 (5pts) | US-075 (13pts) | US-014 (13pts) | US-093 (21pts) | US-014 (21pts) | US-082 (8pts)
US-044 (13pts) | US-093 (5pts) | US-082 (13pts) | US-056 (8pts) | US-077 (3pts) | US-031 (3pts) | US-048 (13pts) | US-088 (3pts) | US-013 (5pts) | US-074 (21pts) | US-010 (13pts) | US-097 (21pts) | US-026 (5pts) | US-003 (13pts) | US-059 (5pts) | US-046 (8pts) | US-062 (21pts) | US-033 (13pts) | US-082 (8pts) | US-010 (8pts)
US-004 (5pts) | US-068 (5pts) | US-010 (5pts) | US-031 (5pts) | US-043 (8pts) | US-009 (3pts) | US-099 (5pts) | US-076 (3pts) | US-026 (3pts) | US-039 (5pts) | US-044 (21pts) | US-009 (21pts) | US-011 (21pts) | US-022 (21pts) | US-030 (13pts) | US-028 (3pts) | US-043 (5pts) | US-093 (21pts) | US-086 (21pts) | US-077 (8pts)
US-081 (3pts) | US-019 (8pts) | US-059 (5pts) | US-022 (3pts) | US-037 (5pts) | US-079 (8pts) | US-030 (3pts) | US-081 (8pts) | US-051 (13pts) | US-086 (3pts) | US-047 (8pts) | US-095 (13pts) | US-005 (13pts) | US-025 (21pts) | US-091 (13pts) | US-068 (5pts) | US-020 (3pts) | US-021 (13pts) | US-070 (5pts) | US-010 (5pts)
US-097 (13pts) | US-099 (21pts) | US-022 (8pts) | US-088 (8pts) | US-030 (3pts) | US-022 (13pts) | US-014 (3pts) | US-074 (8pts) | US-100 (3pts) | US-053 (13pts) | US-068 (13pts) | US-018 (5pts) | US-064 (3pts) | US-060 (5pts) | US-051 (8pts) | US-021 (3pts) | US-084 (3pts) | US-011 (5pts) | US-056 (21pts) | US-025 (13pts)
US-090 (21pts) | US-042 (8pts) | US-069 (5pts) | US-076 (3pts) | US-028 (21pts) | US-041 (3pts) | US-076 (21pts) | US-038 (3pts) | US-011 (21pts) | US-038 (21pts) | US-091 (5pts) | US-025 (21pts) | US-004 (5pts) | US-058 (21pts) | US-018 (13pts) | US-036 (8pts) | US-040 (3pts) | US-083 (8pts) | US-095 (5pts) | US-098 (13pts)
US-064 (21pts) | US-087 (3pts) | US-043 (3pts) | US-055 (8pts) | US-056 (13pts) | US-033 (13pts) | US-011 (3pts) | US-062 (3pts) | US-034 (8pts) | US-034 (8pts) | US-066 (21pts) | US-079 (5pts) | US-018 (5pts) | US-075 (21pts) | US-028 (21pts) | US-073 (5pts) | US-035 (13pts) | US-042 (5pts) | US-095 (8pts) | US-044 (21pts)
US-051 (8pts) | US-086 (21pts) | US-034 (21pts) | US-072 (21pts) | US-082 (13pts) | US-008 (8pts) | US-081 (8pts) | US-077 (5pts) | US-087 (3pts) | US-024 (3pts) | US-009 (3pts) | US-016 (5pts) | US-066 (13pts) | US-088 (3pts) | US-038 (13pts) | US-066 (8pts) | US-004 (3pts) | US-012 (3pts) | US-026 (5pts) | US-097 (5pts)
US-001 (13pts) | US-080 (21pts) | US-080 (13pts) | US-084 (21pts) | US-047 (3pts) | US-025 (5pts) | US-026 (8pts) | US-036 (13pts) | US-083 (3pts) | US-024 (21pts) | US-003 (8pts) | US-037 (13pts) | US-013 (13pts) | US-065 (8pts) | US-082 (21pts) | US-080 (3pts) | US-065 (5pts) | US-071 (13pts) | US-028 (13pts) | US-010 (5pts)
US-009 (5pts) | US-088 (13pts) | US-080 (21pts) | US-087 (3pts) | US-073 (5pts) | US-008 (8pts) | US-017 (8pts) | US-096 (8pts) | US-017 (13pts) | US-005 (5pts) | US-066 (13pts) | US-050 (21pts) | US-081 (3pts) | US-085 (21pts) | US-080 (3pts) | US-052 (8pts) | US-046 (5pts) | US-053 (21pts) | US-083 (13pts) | US-063 (8pts)
US-089 (13pts) | US-061 (8pts) | US-100 (13pts) | US-064 (8pts) | US-026 (13pts) | US-087 (13pts) | US-091 (5pts) | US-013 (21pts) | US-023 (5pts) | US-091 (5pts) | US-095 (8pts) | US-050 (5pts) | US-022 (13pts) | US-008 (8pts) | US-099 (3pts) | US-062 (13pts) | US-056 (3pts) | US-045 (3pts) | US-048 (21pts) | US-026 (5pts)
US-020 (5pts) | US-066 (3pts) | US-050 (5pts) | US-019 (8pts) | US-049 (8pts) | US-070 (13pts) | US-021 (3pts) | US-009 (13pts) | US-060 (3pts) | US-077 (13pts) | US-074 (3pts) | US-024 (8pts) | US-089 (8pts) | US-074 (8pts) | US-033 (13pts) | US-023 (13pts) | US-021 (5pts) | US-055 (3pts) | US-051 (8pts) | US-099 (21pts)
US-040 (3pts) | US-012 (5pts) | US-053 (3pts) | US-034 (5pts) | US-014 (5pts) | US-046 (5pts) | US-089 (3pts) | US-030 (21pts) | US-086 (13pts) | US-063 (3pts) | US-011 (21pts) | US-036 (3pts) | US-070 (8pts) | US-063 (3pts) | US-038 (3pts) | US-094 (13pts) | US-055 (13pts) | US-083 (13pts) | US-097 (13pts) | US-032 (21pts)
US-090 (21pts) | US-073 (5pts) | US-073 (13pts) | US-028 (5pts) | US-045 (13pts) | US-097 (8pts) | US-017 (5pts) | US-094 (5pts) | US-069 (13pts) | US-022 (3pts) | US-060 (13pts) | US-065 (21pts) | US-062 (13pts) | US-046 (3pts) | US-087 (13pts) | US-071 (5pts) | US-003 (3pts) | US-002 (8pts) | US-097 (13pts) | US-003 (3pts)
US-085 (3pts) | US-017 (3pts) | US-093 (5pts) | US-038 (21pts) | US-036 (8pts) | US-099 (3pts) | US-011 (3pts) | US-056 (5pts) | US-090 (21pts) | US-011 (8pts) | US-091 (3pts) | US-085 (21pts) | US-056 (21pts) | US-055 (3pts) | US-019 (21pts) | US-023 (3pts) | US-065 (3pts) | US-098 (8pts) | US-059 (13pts) | US-082 (3pts)
US-053 (5pts) | US-063 (8pts) | US-063 (3pts) | US-042 (3pts) | US-084 (21pts) | US-037 (8pts) | US-015 (8pts) | US-048 (21pts) | US-043 (3pts) | US-074 (21pts) | US-068 (13pts) | US-082 (21pts) | US-085 (5pts) | US-081 (21pts) | US-037 (21pts) | US-033 (21pts) | US-046 (8pts) | US-011 (5pts) | US-017 (5pts) | US-040 (8pts)
US-078 (3pts) | US-033 (21pts) | US-001 (13pts) | US-005 (21pts) | US-080 (5pts) | US-009 (5pts) | US-092 (21pts) | US-049 (8pts) | US-052 (13pts) | US-061 (13pts) | US-100 (3pts) | US-031 (3pts) | US-060 (3pts) | US-068 (8pts) | US-052 (3pts) | US-036 (21pts) | US-093 (5pts) | US-045 (13pts) | US-005 (3pts) | US-054 (3pts)
US-042 (13pts) | US-043 (3pts) | US-058 (13pts) | US-042 (5pts) | US-063 (5pts) | US-025 (21pts) | US-032 (5pts) | US-098 (3pts) | US-032 (3pts) | US-075 (13pts) | US-047 (8pts) | US-009 (21pts) | US-067 (21pts) | US-064 (8pts) | US-051 (8pts) | US-019 (3pts) | US-066 (21pts) | US-069 (5pts) | US-062 (21pts) | US-006 (13pts)
US-083 (21pts) | US-032 (21pts) | US-024 (21pts) | US-086 (21pts) | US-091 (21pts) | US-037 (3pts) | US-055 (13pts) | US-006 (21pts) | US-092 (5pts) | US-037 (3pts) | US-044 (8pts) | US-099 (8pts) | US-023 (3pts) | US-029 (21pts) | US-070 (13pts) | US-081 (3pts) | US-089 (21pts) | US-013 (13pts) | US-031 (5pts) | US-036 (5pts)
US-085 (8pts) | US-050 (21pts) | US-062 (3pts) | US-067 (13pts) | US-010 (13pts) | US-057 (13pts) | US-044 (21pts) | US-044 (21pts) | US-074 (5pts) | US-038 (8pts) | US-016 (5pts) | US-025 (13pts) | US-064 (8pts) | US-076 (21pts) | US-041 (3pts) | US-080 (21pts) | US-074 (5pts) | US-011 (5pts) | US-089 (5pts) | US-016 (13pts)
US-010 (5pts) | US-093 (3pts) | US-068 (13pts) | US-092 (5pts) | US-085 (8pts) | US-044 (5pts) | US-078 (5pts) | US-006 (13pts) | US-051 (3pts) | US-013 (13pts) | US-087 (13pts) | US-037 (8pts) | US-039 (5pts) | US-084 (13pts) | US-058 (13pts) | US-001 (5pts) | US-036 (8pts) | US-063 (3pts) | US-057 (3pts) | US-040 (13pts)
US-097 (8pts) | US-062 (21pts) | US-035 (21pts) | US-021 (3pts) | US-098 (21pts) | US-093 (13pts) | US-063 (13pts) | US-059 (21pts) | US-068 (13pts) | US-016 (8pts) | US-025 (5pts) | US-099 (21pts) | US-076 (8pts) | US-075 (5pts) | US-072 (5pts) | US-045 (8pts) | US-099 (21pts) | US-029 (5pts) | US-048 (5pts) | US-074 (21pts)
US-080 (13pts) | US-073 (8pts) | US-057 (3pts) | US-041 (21pts) | US-043 (8pts) | US-014 (13pts) | US-001 (21pts) | US-066 (8pts) | US-006 (21pts) | US-039 (3pts) | US-027 (8pts) | US-082 (5pts) | US-014 (5pts) | US-035 (3pts) | US-097 (5pts) | US-039 (5pts) | US-041 (3pts) | US-087 (21pts) | US-021 (5pts) | US-022 (21pts)
US-059 (8pts) | US-018 (3pts) | US-097 (3pts) | US-007 (3pts) | US-065 (13pts) | US-048 (13pts) | US-059 (8pts) | US-049 (3pts) | US-038 (21pts) | US-052 (8pts) | US-012 (3pts) | US-007 (13pts) | US-014 (21pts) | US-036 (13pts) | US-004 (13pts) | US-015 (8pts) | US-071 (8pts) | US-033 (13pts) | US-063 (21pts) | US-097 (5pts)
US-016 (21pts) | US-090 (5pts) | US-001 (21pts) | US-069 (21pts) | US-027 (21pts) | US-012 (5pts) | US-018 (3pts) | US-038 (13pts) | US-061 (8pts) | US-087 (21pts) | US-081 (13pts) | US-050 (8pts) | US-081 (8pts) | US-031 (8pts) | US-058 (13pts) | US-062 (5pts) | US-036 (3pts) | US-065 (13pts) | US-091 (13pts) | US-013 (3pts)
US-010 (8pts) | US-010 (13pts) | US-096 (8pts) | US-091 (3pts) | US-076 (3pts) | US-067 (5pts) | US-042 (5pts) | US-077 (21pts) | US-058 (8pts) | US-016 (3pts) | US-082 (8pts) | US-045 (8pts) | US-004 (3pts) | US-079 (8pts) | US-099 (8pts) | US-079 (13pts) | US-026 (5pts) | US-074 (3pts) | US-006 (3pts) | US-024 (5pts)
US-093 (21pts) | US-023 (13pts) | US-013 (21pts) | US-048 (3pts) | US-034 (13pts) | US-062 (3pts) | US-007 (21pts) | US-068 (13pts) | US-083 (13pts) | US-070 (21pts) | US-070 (8pts) | US-064 (5pts) | US-002 (13pts) | US-005 (21pts) | US-007 (21pts) | US-014 (21pts) | US-074 (13pts) | US-077 (5pts) | US-064 (3pts) | US-093 (8pts)
US-020 (21pts) | US-013 (13pts) | US-088 (3pts) | US-039 (8pts) | US-024 (21pts) | US-093 (5pts) | US-097 (21pts) | US-039 (3pts) | US-061 (13pts) | US-068 (3pts) | US-050 (3pts) | US-020 (3pts) | US-007 (21pts) | US-006 (3pts) | US-023 (21pts) | US-019 (5pts) | US-055 (5pts) | US-073 (5pts) | US-084 (13pts) | US-058 (8pts)
US-049 (13pts) | US-044 (5pts) | US-093 (21pts) | US-069 (8pts) | US-030 (5pts) | US-011 (3pts) | US-058 (21pts) | US-068 (8pts) | US-094 (21pts) | US-012 (8pts) | US-012 (5pts) | US-076 (21pts) | US-044 (21pts) | US-050 (3pts) | US-017 (3pts) | US-092 (8pts) | US-068 (5pts) | US-012 (8pts) | US-002 (21pts) | US-034 (8pts)
US-067 (3pts) | US-050 (3pts) | US-029 (3pts) | US-057 (5pts) | US-033 (8pts) | US-020 (21pts) | US-081 (3pts) | US-045 (8pts) | US-098 (3pts) | US-086 (3pts) | US-022 (5pts) | US-021 (8pts) | US-055 (5pts) | US-049 (21pts) | US-046 (8pts) | US-021 (13pts) | US-051 (13pts) | US-058 (3pts) | US-014 (21pts) | US-001 (13pts)
US-016 (21pts) | US-040 (8pts) | US-054 (5pts) | US-010 (13pts) | US-002 (5pts) | US-066 (13pts) | US-068 (21pts) | US-091 (5pts) | US-091 (13pts) | US-036 (5pts) | US-097 (13pts) | US-041 (3pts) | US-091 (3pts) | US-013 (5pts) | US-025 (8pts) | US-010 (3pts) | US-026 (5pts) | US-061 (21pts) | US-005 (3pts) | US-013 (5pts)

## Epic Roadmap
EPIC ROADMAP & TIMELINE
Epic ID | Epic Name | Stories | Total Points | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
EP-001 | Data Setup | 4 | 12 | 12 | 0 | 0 | 0 | 0
EP-002 | EDA | 7 | 63 | 33 | 30 | 0 | 0 | 0
EP-003 | Data Processing | 6 | 58 | 0 | 17 | 41 | 0 | 0
EP-004 | Modeling | 6 | 62 | 0 | 0 | 3 | 59 | 0
EP-005 | Insights | 6 | 45 | 0 | 0 | 0 | 21 | 24
EP-006 | Visualization | 2 | 29 | 0 | 0 | 0 | 0 | 29
EP-007 | Documentation | 4 | 42 | 0 | 0 | 0 | 0 | 42
EP-008 | QA | 3 | 26 | 0 | 0 | 0 | 0 | 26
TOTAL |  | 38 | 337 | 45 | 47 | 44 | 80 | 121