## Sheet1
ID | Epic | User Story Title | Priority | Role | Requirement | Benefit | Estimation | Dependencies
US-001 | Data Acquisition & Setup | Dataset Download & Validation | P0 - Critical | Data Analyst | Download enrolment, demographic & biometric datasets; validate schema & integrity | Enable EDA and ensure data completeness | 3 | None
US-002 | Data Acquisition & Setup | Development Environment Configuration | P0 - Critical | Developer | Set up Python 3.9+, libraries, Jupyter, Git repo, requirements file | Reproducible and conflict-free development | 2 | None
US-003 | Data Acquisition & Setup | Data Storage & Access Strategy | P1 - High | Data Engineer | Implement shared storage, fast access utilities, backup strategy | Enable team access and fast query performance | 5 | US-001
US-004 | Data Acquisition & Setup | Collaborative Documentation Setup | P1 - High | Project Manager | Set up shared documentation platform & templates | Enable structured team collaboration | 2 | None
US-005 | EDA | Data Quality Assessment | P0 - Critical | Data Analyst | Missing values, duplicates, outliers, type consistency report | Ensure reliable downstream analysis | 8 | US-001,US-002
US-006 | EDA | Temporal Trend Analysis | P0 - Critical | Data Analyst | Monthly trends, seasonality, YoY growth, anomaly periods | Identify patterns and time-based insights | 13 | US-005
US-007 | EDA | Geographic Distribution Analysis | P0 - Critical | Data Analyst | State/district choropleths, hotspot analysis, inequality metrics | Identify regional disparities | 13 | US-005
US-008 | EDA | Demographic Pattern Analysis | P1 - High | Data Analyst | Age-group, gender, cohort, population pyramid analysis | Understand segment engagement | 8 | US-005
US-009 | EDA | Update Type Characterization | P1 - High | Data Analyst | Compare demographic vs biometric update behaviors | Understand update drivers | 8 | US-006,US-007
US-010 | EDA | Anomaly Detection in EDA | P1 - High | Data Analyst | Statistical anomaly detection & visualization dashboard | Detect unusual patterns | 13 | US-006,US-007
US-011 | Data Engineering | Data Cleaning Pipeline | P0 - Critical | Data Engineer | Automated cleaning, imputation, formatting, encoding | Standardized clean datasets | 13 | US-005
US-012 | Feature Engineering | Temporal Features | P0 - Critical | Data Scientist | Year, month, lag, rolling averages, seasonality indicators | Improve time-aware modeling | 8 | US-011
US-013 | Feature Engineering | Geographic Features | P1 - High | Data Scientist | State/district aggregates, clustering, spatial lags | Enable spatial modeling | 13 | US-011
US-014 | Feature Engineering | Rate & Ratio Features | P1 - High | Data Scientist | Enrolment rates, update ratios, growth rates | Normalized comparative metrics | 8 | US-011
US-015 | Feature Engineering | Feature Selection & Dimensionality Reduction | P2 - Medium | Data Scientist | Correlation removal, RFE, PCA, feature importance | Efficient & interpretable models | 8 | US-012,US-013,US-014
US-016 | Modeling | Baseline Models | P0 - Critical | Data Scientist | Naive forecast, linear regression, moving average | Create benchmark performance | 5 | US-011
US-017 | Modeling | Time Series Forecasting | P0 - Critical | Data Scientist | ARIMA/SARIMA & Prophet forecasting | Predict 6-month enrolment trends | 13 | US-012,US-016
US-018 | Modeling | ML Regression Models | P1 - High | Data Scientist | Random Forest, XGBoost, LightGBM + tuning | Identify best predictive model | 13 | US-015,US-016
US-019 | Modeling | Anomaly Detection Models | P1 - High | Data Scientist | Isolation Forest, LOF, DBSCAN models | Automated anomaly flagging | 13 | US-015
US-020 | Modeling | Regional Classification Model | P2 - Medium | Data Scientist | Classify regions into behavioral archetypes | Enable targeted interventions | 8 | US-015
US-021 | Modeling | Model Validation & Testing | P0 - Critical | Data Scientist | Holdout testing, CV, learning curves, leakage checks | Ensure reliability & credibility | 5 | US-017,US-018,US-019
US-022 | Insights | Demographic Trend Report | P0 - Critical | Analyst | Comprehensive demographic insights report | Actionable segment strategy | 8 | US-008
US-023 | Insights | Geographic Disparity Report | P0 - Critical | Analyst | Document inequalities & adoption patterns | Resource allocation guidance | 8 | US-007
US-024 | Insights | Temporal & Seasonality Report | P1 - High | Analyst | Document seasonal patterns & growth shifts | Optimize campaign timing | 5 | US-006,US-017
US-025 | Insights | Anomaly Investigation Report | P1 - High | Analyst | Investigate top anomalies & root causes | Corrective action planning | 8 | US-010,US-019
US-026 | Insights | Predictive Insights & Forecast Report | P1 - High | Analyst | Translate forecasts into resource planning | Proactive decision making | 8 | US-017,US-018
US-027 | Insights | Update Behavior Analysis | P2 - Medium | Analyst | Analyze update journeys & user personas | Improve update experience | 8 | US-009
US-028 | Visualization | Static Visualization Library | P0 - Critical | Data Analyst | Create 15-20 publication-quality charts | Support reports & presentations | 8 | US-006,US-007,US-008
US-029 | Dashboard | Interactive Dashboard Development | P1 - High | Stakeholder | Multi-page dashboard with filters & drilldowns | Dynamic exploration of insights | 21 | US-011,US-022,US-023,US-024
US-030 | Dashboard | Geospatial Visualization Enhancement | P1 - High | User | Interactive maps with drilldown & tooltips | Visual geographic analysis | 8 | US-029
US-031 | Presentation | Slide Deck Creation | P0 - Critical | Presenter | 25-35 professional slides | Effective communication to judges | 13 | US-022,US-023,US-024,US-025,US-026
US-032 | Documentation | Methodology Documentation | P0 - Critical | Team | Document preprocessing, modeling & validation | Reproducibility & scientific rigor | 8 | US-011,US-017,US-018
US-033 | Documentation | Code Documentation & Repo Setup | P0 - Critical | Evaluator | GitHub repo with structure, README & license | Technical transparency | 8 | All Coding Tasks
US-034 | Documentation | Executive Summary | P0 - Critical | Decision-Maker | 2-3 page concise summary | Quick leadership understanding | 5 | US-022,US-023,US-024,US-025,US-026
US-035 | Documentation | Technical Report | P1 - High | Technical Reviewer | 10-15 page academic-style report | Evaluate rigor & innovation | 13 | US-032
US-036 | Documentation | Dataset Description Documentation | P0 - Critical | Evaluator | Complete data dictionary & source references | Alignment with hackathon rules | 5 | US-001,US-005
US-037 | Documentation | Video Presentation | P2 - Medium | Participant | 5-10 min demo & narration video | Enhance submission impact | 5 | US-031